## Form Responses 1
Timestamp | Untitled Question

## Sheet1
Last Update | 2019-04-22
Author | Adrian Monges
Email | among003@ucr.edu
Description | FeFlask - ManageBudget is a mobile app that allows you to manage your expenses by setting budget profiles and notifications. The app also helps you view your expenses through csv files and dynamic charts. The ManageBudget mobile app also lets you split expenses with others.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
SPRINT # 1
Tabs | Notes | User Stories | Story Point (1- 5)
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points) | I want to be able to login and access my account and data | 3
| Depending on the amount of story points, some stories may need to be split into smaller stories | I want to be able to input a budget/spending limit and set up automated/periodic expenses | 5
| Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell) | I want to be able to input credits and expenses | 4
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog) | To Do | In Progress |  | To Verify | Done
| Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours | Tasks | Tasks | Assigned | Verifying | Tasks | Assigned | Verified By
| Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell) | Landing Page
| Perform task assignments at the Sprint Planning Meeting | Authentication
| During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name | Main Page
| Inform your teammates know before you pull a task from "To Do" list | Firebase Data Access
| "To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing | Budget Sub Menu
| A task in "Done" list should have its verifier's name appended | Credits And Expenses Sub Menu
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress