## Form Responses 2
Timestamp | Untitled Question

## Sheet1
Last Update | 2019-05-06
Author | Adrian Monges
Email | among003@ucr.edu
Description | FeFlask - ManageBudget is a mobile app that allows you to manage your expenses by setting budget profiles and notifications. The app also helps you view your expenses through csv files and dynamic charts. The ManageBudget mobile app also lets you split expenses with others.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
SPRINT # 2
Tabs | Notes | User Stories | Definition | Story Point (1- 5)
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points) | As a user, I want to be able to categorize and describe items in my budget. | - We want to be able to assign each budget category a color from a preselected set of colors. -Describing is a more specific description for an expense category entry. -When you click on a budget page, I want to be able to see all the expense entries associated with the budget | 4
| Depending on the amount of story points, some stories may need to be split into smaller stories | As a user, I want reminders/push notifications about approaching my budget | - After you enter an expense, they app checks how close you are to your budget, then sends a notification based on how close (80%) you are to the spending limit. -Push notification if there was an error, when we push to firebase. | 3
| Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell) | As a user, I want to see my budget visually represented in a dynamic chart. (Pie chart or histogram) | - I want the visual graph to corretly display by color within the Main page - I want a dynamic multicolored percentage bar that visually represents my expenses against the budget on the budget page. | 4
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog) | To Do |  | In Progress |  | To Verify | Done
| Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours | Tasks |  | Tasks | Assigned | Verifying | Tasks | Assigned | Verified By
| Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell) | Firebase Fix Realtime |  |  | Takbir |  | Landing Page | Takbir Islam | /all
| Perform task assignments at the Sprint Planning Meeting | Fix Authentication Glitch |  |  | Takbir |  | Authentication | Takbir Islam | /all
| During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name | Login Page - Verification and Prompts |  |  | Adrian |  | Main Page | Adrian Monges | /all
| Inform your teammates know before you pull a task from "To Do" list | Assign Color - Budget |  |  | Andy/Adrian |  | Firebase Data Access | Takbir Islam (done) | /all
| "To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing | Push Notification |  |  | Uy//Takbir |  | Budget Sub Menu | Andy Nguyen | /all
| A task in "Done" list should have its verifier's name appended | Detailed Budget Category View |  |  | Andy/Adrian |  | Credits And Expenses Sub Menu | Winson Bi | /all
|  | Budget Page - Dynamic Chart |  |  | Andy/Adrian
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting | Main Page- Dynamic Chart |  |  | Winson
|  | Credits and Expenses Page |  |  | Winson
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart" | Refactoring/Cleaning UI |  |  | /all
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Form Responses 1
Timestamp | Untitled Question