## Form Responses 2
Timestamp | Untitled Question

## Sheet1
Last Update | 2019-05-06
Author | Adrian Monges
Email | among003@ucr.edu
Description | FeFlask - ManageBudget is a mobile app that allows you to manage your expenses by setting budget profiles and notifications. The app also helps you view your expenses through csv files and dynamic charts. The ManageBudget mobile app also lets you split expenses with others.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
SPRINT # 2
Tabs | Notes | User Stories | Definition | Story Point (1- 5)
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points) | As a user, I want to be able to share my budget/expenses with other people using the app | -Have a button when creating a category that allows the you to share the budget with users by the recipient's email. -Accesses a firebase list of all users that has corresponding user emails and user keys -Accessing budgets shared with you are done by clicking a "Look at Shared Things" button | 5
| Depending on the amount of story points, some stories may need to be split into smaller stories | As a user, I want to be able to export my budget and expenses(csv file) | -There will be a button in Credits and Expenses to export my budget and expenses in a CSV file -The CSV is sent as an Email and Text | 3
| Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell) | As a user, I want to be able to delete things | -I want to be able to delete budgets categories on the budgets page -I want to be able to delete expenses on both the budgets page and the CreditsAndExpenses Page -I want to be able to delete credits on the CreditsAnd Expenses Page | 3
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog) | To Do |  | In Progress |  | To Verify | Done
| Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours | Tasks |  | Tasks | Assigned | Verifying | Tasks | Assigned | Verified By
| Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell) | Add Share budget button on "Create Budgets" Pop up |  |  | Adrian |  | Landing Page | Takbir Islam | /all
| Perform task assignments at the Sprint Planning Meeting | Add Firebase Database Node "Shared Budget" |  |  | Takbir/Winson |  | Authentication | Takbir Islam | /all
| During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name | Add "View Shared Budgets" Button and page |  |  | Andy/Adrian |  | Main Page | Adrian Monges | /all
| Inform your teammates know before you pull a task from "To Do" list | Be able to add expenses to shared budgets |  |  | Winson Bi |  | Firebase Data Access | Takbir Islam (done) | /all
| "To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing | Export CSV |  |  | Uy/Takbir |  | Budget Sub Menu | Andy Nguyen | /all
| A task in "Done" list should have its verifier's name appended | Add a way to edit/delete an expense and credits from Credits and Expenses "View Detailed", Add a way to edit/delete a category from budgets page |  |  | Winson Bi/Andy |  | Credits And Expenses Sub Menu | Winson Bi | /all
|  | Update Firebase Functionalities |  |  | Takbir |  | Firebase Fix Realtime | Takbir | /all
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting | [5 empty] | Fix Authentication Glitch | Takbir | /all
[7 empty] | Login Page - Verification and Prompts | Adrian | /all
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart" | [5 empty] | Assign Color - Budget | Andy/Adrian | /all
| if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress | [5 empty] | Push Notification | Uy/Takbir | /all
[7 empty] | Detailed Budget Category View | Andy/Adrian | /all
[7 empty] | Budget Page - Dynamic Chart | Andy/Adrian | /all
[7 empty] | Main Page- Dynamic Chart | Winson | /all
[7 empty] | Credits and Expenses Page | Winson | /all
[7 empty] | Refactoring/Cleaning UI | /all | /all

## Form Responses 1
Timestamp | Untitled Question